## Genel Ozet
CRM WorkTrack - Birlesik Frontend Roadmap
Proje Ozet Bilgisi
Amac | Mevcut backend endpoint'lerine dogrudan baglanan, sunumda gosterebilecegin temiz ve hizli gelistirilebilir frontend plani.
Odak | Abartisiz ama profesyonel: Login + Layout + Dashboard + Customers + Jobs + Job Detail + Comments + Timeline.
Backend Durumu | Auth, dashboard metrics, customers, jobs, comments, timeline, filtering ve restore endpoint'leri hazir.
Frontend Hedefi | API baglantili admin panel kurmak; kritik ekranlari once cikarip sonra polish eklemek.
Onerilen Stack | React + Vite + React Router + Axios + React Hook Form + TanStack Query (opsiyonel) + Bootstrap veya MUI.
Teslim Stratejisi | Ilk teslimde calisan akis: Login -> Dashboard -> Customers -> Jobs -> Job Detail. Sonra comments/timeline polish.
En Onemli Sayfalar
Oncelik | Sayfa | Neden Var? | Sunum Degeri | Durum | Not
1 | Login | JWT token alma, route guard baslatma | Yuksek | Planlandi | Bu sayfa backend gucunu en iyi gosterir
2 | Dashboard | Tum metrikleri ve analiz kartlarini tek yerde gostermek | Yuksek | Planlandi | Bu sayfa backend gucunu en iyi gosterir
3 | Customers | CRUD, search, soft delete / restore | Yuksek | Planlandi | Bu sayfa backend gucunu en iyi gosterir
4 | Jobs | Advanced filtering, status, priority, pagination | Yuksek | Planlandi | Bu sayfa backend gucunu en iyi gosterir
5 | Job Detail | Detay, timeline, comments, activity log | Yuksek | Planlandi | Bu sayfa backend gucunu en iyi gosterir
Kaynak Notu | Bu workbook, kullanicinin onceki 11 haftalik planindaki frontend fazlarini ve endpoint bazli frontend haritasini tek yapida birlestirir.

## Ana Frontend Roadmap
Ana Frontend Roadmap - Sayfa, Bilesen ve Endpoint Baglantisi
Faz | Oncelik | Sayfa / Ekran | Ana Bilesenler | Baglanacak Endpointler | State / Service | Bagimlilik | Kabul Kriteri | Cikti
Faz 1 | 1 | Login | Login formu, hata mesaji, loading state | POST /api/auth/login | authService, authStore | Token saklama + route guard | Basarili login sonrasi dashboard'a yonlenme | Calisan giris akisi
Faz 1 | 2 | App Layout | Sidebar, topbar, protected routes, logout | Endpoint yok | layout/, routes/ | Login sayfasi | Korumali route'lar token olmadan acilmaz | Admin panel iskeleti
Faz 1 | 3 | Dashboard | KPI kartlari, chart alanlari, recent widgets | GET /api/dashboard ¦ /job-status-distribution ¦ /jobs-by-priority ¦ /jobs-per-customer ¦ /recent-activities ¦ /recent-jobs ¦ /overdue ¦ /unassigned ¦ /due-soon | dashboardService | Login + layout | Tum widget'ler veri cekip bos state / loading state gosterir | Vitrin ekran
Faz 2 | 4 | Customers List | Table, search box, status filtresi, pagination, action butonlari | GET /api/customers ¦ GET /api/customers?q= ¦ DELETE /api/customers/{id} ¦ POST /api/customers/{id}/restore | customerService | Layout | Liste, arama ve aktif/pasif akisi calisir | CRM customer paneli
Faz 2 | 5 | Customer Form | Create / Edit modal veya sayfa, validation | POST /api/customers ¦ PUT /api/customers/{id} | customerService, forms/ | Customers list | Musteri ekleme ve guncelleme calisir | Customer CRUD UI
Faz 3 | 6 | Jobs List | Advanced filter bar, table, badges, pagination | GET /api/jobs?status=&priority=&dueDateFrom=&dueDateTo=&q= | jobService | Customers verisi (opsiyonel select) | Filtreler birlesik sekilde calisir | Is yonetim paneli
Faz 3 | 7 | Job Form | Create / Edit, customer select, priority/status select, due date | POST /api/jobs ¦ PUT /api/jobs/{id} | jobService, forms/ | Jobs list | Yeni job ekleme ve duzenleme calisir | Job CRUD UI
Faz 3 | 8 | Job Action Panel | Assign button, status update action | POST /api/jobs/{id}/assign ¦ POST /api/jobs/{id}/status | jobService | Job detail veya list row action | Atama ve status guncelleme calisir | Akis yonetimi
Faz 4 | 9 | Job Detail | Genel bilgi karti, badges, metadata | GET /api/jobs/{id} | jobService | Jobs list | Detay sayfasi veriyi dogru gosterir | Detay ekran
Faz 4 | 10 | Comments Panel | Comment list, add, update, delete | GET /api/jobs/{jobId}/comments ¦ POST /api/jobs/{jobId}/comments ¦ PUT /api/jobs/{jobId}/comments/{id} ¦ DELETE /api/jobs/{jobId}/comments/{id} | commentService | Job detail | Comment CRUD ve local refresh calisir | Canli iletisim hissi
Faz 4 | 11 | Timeline / Activity | Timeline listesi, activity cards | GET /api/jobs/{id}/timeline ¦ GET /api/jobs/{id}/activities-log | jobService | Job detail | Zaman cizelgesi sirali ve okunur sekilde gelir | Audit gorunumu
Faz 5 | 12 | Polish / UX | Loading skeleton, empty state, toast, badge colors | Var olan endpointler | shared/components | Tum ana sayfalar | Uygulama kesintisiz deneyim verir | Demo hazir UI

## Sayfa-Endpoint Haritasi
Sayfa -> Endpoint -> UI Bileseni Haritasi
Sayfa | Widget / Islev | Endpoint | Method | UI Bileseni | Ne Gosterilecek? | Oncelik | Not
Login | Giris | /api/auth/login | POST | Form + Button | JWT token | Yuksek | Ilk ekran
Dashboard | Summary Cards | /api/dashboard | GET | KPI cards | Toplam customer/job ve durumlar | Yuksek | Acilis vitrini
Dashboard | Status Chart | /api/dashboard/job-status-distribution | GET | Pie/Bar chart | Open/InProgress/Completed/Cancelled | Yuksek | Sunumluk
Dashboard | Priority Chart | /api/dashboard/jobs-by-priority | GET | Doughnut/Bar | High/Medium/Low | Orta | Yeni eklenen endpoint
Dashboard | Jobs per Customer | /api/dashboard/jobs-per-customer | GET | Horizontal bar | Musteri bazli is sayisi | Orta | Analitik
Dashboard | Recent Activities | /api/dashboard/recent-activities | GET | Activity list | Son hareketler | Orta | Canlilik katar
Dashboard | Recent Jobs | /api/dashboard/recent-jobs | GET | Mini table/list | Son olusturulan isler | Orta | Kullanisli
Dashboard | Overdue Card | /api/dashboard/overdue | GET | KPI card | Deadline'i gecen isler | Orta | Risk takibi
Dashboard | Unassigned Card | /api/dashboard/unassigned | GET | KPI card | Atanmamis isler | Orta | Operasyonel takip
Dashboard | Due Soon Card | /api/dashboard/due-soon | GET | KPI card | 7 gun icinde bitecek isler | Orta | Planlama
Customers | Liste / Search | /api/customers?q=&page=&pageSize= | GET | Table + search input | Musteri listesi | Yuksek | Search zaten backend'de var
Customers | Create | /api/customers | POST | Drawer/Modal form | Yeni musteri | Yuksek | Form validation
Customers | Update | /api/customers/{id} | PUT | Edit form | Musteri guncelleme | Yuksek | Reuse form
Customers | Soft Delete | /api/customers/{id} | DELETE | Action button | Pasife cekme | Orta | Hard delete yok
Customers | Restore | /api/customers/{id}/restore | POST | Action button | Pasif musteriyi aktive etme | Orta | Enterprise hissi
Jobs | Liste / Filter | /api/jobs?status=&priority=&dueDateFrom=&dueDateTo=&q= | GET | Table + filter bar | Advanced filtered job list | Yuksek | En guclu ekran
Jobs | Create | /api/jobs | POST | Job form | Yeni job | Yuksek | Customer secimi gerekli
Jobs | Update | /api/jobs/{id} | PUT | Edit form | Job guncelleme | Yuksek | Status/priority duzenleme
Jobs | Assign | /api/jobs/{id}/assign | POST | Action menu | Kullaniciya atama | Orta | Opsiyonel ilk versiyonda
Jobs | Status Update | /api/jobs/{id}/status | POST | Badge action / modal | Status degisimi | Orta | Opsiyonel ilk versiyonda
Job Detail | Detay | /api/jobs/{id} | GET | Info cards | Tum job alanlari | Yuksek | Listeden detail'e gecis
Job Detail | Timeline | /api/jobs/{id}/timeline | GET | Timeline component | Sirali olaylar | Yuksek | Yeni eklenen endpoint
Job Detail | Activity Log | /api/jobs/{id}/activities-log | GET | History list | Detayli log | Dusuk | Timeline varsa ikinci planda
Comments | List/Add | /api/jobs/{jobId}/comments | GET + POST | Comments box | Yorumlar | Orta | Job detail icinde
Comments | Edit/Delete | /api/jobs/{jobId}/comments/{id} | PUT + DELETE | Inline actions | Yorum duzenleme/silme | Orta | Kucuk ama degerli

## Sprint Plan
Uygulama Sprint Plani - Frontend Gelistirme Sirasi
Sprint | Sure | Hedef | Sayfalar | Kritik Endpointler | Teslim Ciktisi | Bagli Onceki Adim | Not
Sprint 1 | 2-3 gun | Auth + Layout temelini kur | Login, Protected Layout | POST /api/auth/login | Login calisir, token saklanir, sidebar/topbar hazir | Yok | En once yap
Sprint 2 | 2-3 gun | Dashboard vitrini cikar | Dashboard | /api/dashboard ve tum dashboard endpointleri | Kartlar + grafikler + recent listeler calisir | Sprint 1 | Sunum etkisi en yuksek
Sprint 3 | 2-3 gun | Customers modulu | Customers list, Customer form | /api/customers ¦ /restore | Arama, ekleme, guncelleme, pasifleştirme, restore | Sprint 1 | CRUD tamamlanir
Sprint 4 | 3-4 gun | Jobs listeleme ve filtreleme | Jobs list, Job form | /api/jobs | Advanced filtering ve tablolu job yonetimi | Sprint 1 + 3 | Backend gucunu gosterir
Sprint 5 | 2-3 gun | Job detail deneyimi | Job detail, Comments, Timeline | /api/jobs/{id} ¦ /timeline ¦ /comments | Detay, yorumlar ve gecmis tek sayfada | Sprint 4 | Sunumda guclu durur
Sprint 6 | 1-2 gun | Polish ve demo akisi | Tum ana sayfalar | Var olan endpointler | Loading, empty state, toast, role/route kontrolu | Tum sprintler | Final sunum hazirligi
11 Haftalik Plan ile Baglanti
Mevcut Hafta | Orijinal Odak | Bu Frontend Plandaki Karsiligi | Hangi Sayfada Gozukuyor? | Not
Hafta 10 | Frontend Panel Gelistirme | Sprint 1-4 | Login, Layout, Dashboard, Customers, Jobs | Senin frontend ana islerin burada toparlaniyor
Hafta 11 | Son Testler ve Sunum | Sprint 5-6 | Job Detail, Comments, Timeline, Polish | Demo akisi ve final polish burada

## Klasor Yapisi
React Klasor ve Servis Yapisi
Katman | Onerilen Yol | Icerik | Bagli Sayfalar | Bagli Service | Not
App | src/app/ | router, providers, app config | Tum sayfalar | - | Genel giris noktasi
Layouts | src/layouts/ | MainLayout, AuthLayout, Sidebar, Topbar | Dashboard, Customers, Jobs | - | Protected route ile birlikte
Pages | src/pages/auth/ | LoginPage.jsx | Login | authService | Tek ekran
Pages | src/pages/dashboard/ | DashboardPage.jsx | Dashboard | dashboardService | Kart + grafik sayfasi
Pages | src/pages/customers/ | CustomersPage.jsx, CustomerForm.jsx | Customers | customerService | Liste + form
Pages | src/pages/jobs/ | JobsPage.jsx, JobForm.jsx, JobDetailPage.jsx | Jobs, Job Detail | jobService, commentService | En buyuk modul
Components | src/components/common/ | Table, SearchBar, StatusBadge, EmptyState, Loader | Tum sayfalar | - | Tekrar kullanilabilir UI
Components | src/components/dashboard/ | KpiCard, ChartCard, ActivityList | Dashboard | dashboardService | Gorsel duzen
Components | src/components/jobs/ | JobFilters, JobTimeline, CommentList, CommentForm | Jobs / Job Detail | jobService, commentService | Detay ve filtreler
Services | src/services/ | authService, dashboardService, customerService, jobService, commentService | Tum sayfalar | Axios instance | Endpoint baglantisi burada
Store | src/store/ | authStore, uiStore (opsiyonel) | Tum sayfalar | - | Token ve temel UI state
Utils | src/utils/ | date, token, query helpers | Tum sayfalar | - | Yardimci fonksiyonlar